## Sheet1
GANTT CHART
Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 79
Project scope and objectives
Reserch Market trend and customer requirements
Create user stories
Create class diagrem
Create EER diagrem
Create wireframes
Communicate deliverables
Design application styles
Design UI/UX mockups (Web Applicatin)
Design UI/UX mockups (Mobile Applicatin)
Review design artifacts
Setup environments (Dev, QA, Test) for web application backend
Setup environments (Dev, QA, Test) for mobile application backend
Impliment web application front-end
Impliment mobile application UI
Impliment backend for web application
Impliment backend for mobile application
Integrate payment gateway
Impliment Cart and checkout function in both front-end and backend
Deploy artifacts to QA and Test environment
Perform unit tests
Perform integration tests
Perform load/ stress tests
Perform functinal requirement testing
Perform UAT testing
Setup environment
Deploy backend and front end to the prod environment
Upload mobile application to playstore and app store
Run prod test
Create handover documentation
Create training materials
Monitor matrics
Plan for future implementations