## Sheet1
PROJECT TITILE |  |  | E-commerce Application
COMPNY NAME |  |  | ABC
DATE |  |  | 2025-10-20
PROJECT MANAJER |  |  | SAHAN
TECHNICAL WRITERS |  |  | SAHAN, KASUN, KAVINDA, MILA
PROJECT DETAILS | [7 empty] | DELIVERABLE
STATUS | PRIORITY | START DATE | END DATE | DURATION (DAYS) | TASK NO | TASK NAME | INCHARGE | DELIVERABLE | DONE
PROJECT PLANING STAGE
DONE | HIGH | 2025-01-07 | 2025-03-07 | 3 | 1 | Project scope and objectives | Sahan | Document | 100%
DONE | HIGH | 2025-04-07 | 2025-06-07 | 2 | 2 | Reserch Market trend and customer requirements | Kavinda, Sahan | Document | 100%
DONE | HIGH | 2025-07-07 | 2025-10-07 | 3 | 3 | Create user stories | Kasun | Document | 100%
DONE | HIGH | 2025-11-07 | 13/7/2025 | 2 | 4 | Create class diagrem |  |  | 100%
DONE | MEDIUM | 14/7/2025 | 16/7/2025 | 2 | 5 | Create EER diagrem |  |  | 100%
DONE | MEDIUM | 17/7/2025 | 19/7/2025 | 2 | 6 | Create wireframes |  |  | 100%
DONE | MEDIUM | 20/7/2025 | 21/7/2025 | 1 | 7 | Communicate deliverables |  |  | 100%
DESIGNING STAGE
DONE | MEDIUM | 22/7/2025 | 23/7/2025 | 1 | 8 | Design application styles | Kavinda | Photoshop file | 100%
DONE | HIGH | 24/7/2025 | 28/7/2025 | 4 | 9 | Design UI/UX mockups (Web Applicatin) | Kasun | Figma Design | 100%
DONE | HIGH | 29/7/2025 | 31/7/2025 | 2 | 10 | Design UI/UX mockups (Mobile Applicatin) | Kasun | Figma Design | 100%
DONE | MEDIUM | 2025-01-08 | 2025-01-08 | 1 | 11 | Review design artifacts | Sahan, Kasun, Kavinda |  | 100%
PROJECT DEVELOPMENT STAGE
DONE | HIGH | 2025-02-08 | 2025-04-08 | 2 | 12 | Setup environments (Dev, QA, Test) for web application backend | Kavinda |  | 100%
DONE | HIGH | 2025-05-08 | 2025-07-08 | 2 | 13 | Setup environments (Dev, QA, Test) for mobile application backend | Kasun |  | 100%
DONE | HIGH | 2025-08-08 | 15/8/2025 | 6 | 14 | Impliment web application front-end | Kasun |  | 100%
IN PROGRESS | HIGH | 16/8/2025 | 19/8/2025 | 3 | 15 | Impliment mobile application UI | Kavinda |  | 80%
NOT YET STARTED | HIGH | 20/8/2025 | 25/8/2025 | 5 | 16 | Impliment backend for web application | Kasun |  | 0%
NOT YET STARTED | HIGH | 26/8/2025 | 30/8/2025 | 4 | 17 | Impliment backend for mobile application | Kavinda |  | 0%
NOT YET STARTED | HIGH | 31/8/2025 | 31/8/2025 | 1 | 18 | Integrate payment gateway | Kasun |  | 0%
NOT YET STARTED | HIGH | 2025-01-09 | 2025-03-09 | 2 | 19 | Impliment Cart and checkout function in both front-end and backend | Kasun, Kavinda |  | 0%
PROJECT TESTING STAGE
NOT YET STARTED | HIGH | 2025-03-09 | 2025-05-09 | 2 | 20 | Deploy artifacts to QA and Test environment | Kavinda, Kasun |  | 0%
NOT YET STARTED | MEDIUM | 2025-06-09 | 2025-09-09 | 3 | 21 | Perform unit tests | Mila |  | 0%
NOT YET STARTED | MEDIUM | 2025-10-09 | 2025-12-09 | 2 | 22 | Perform integration tests | Mila |  | 0%
NOT YET STARTED | MEDIUM | 13/9/2025 | 15/9/2025 | 2 | 23 | Perform load/ stress tests | Mila |  | 0%
NOT YET STARTED | HIGH | 16/9/2025 | 20/9/2025 | 4 | 24 | Perform functinal requirement testing | Mila |  | 0%
NOT YET STARTED | HIGH | 21/9/2025 | 26/9/2025 | 5 | 25 | Perform UAT testing | Mila |  | 0%
PROJECT DEPLOY AND HANDOVER STAGE
NOT YET STARTED | HIGH | 27/9/2025 | 28/9/2025 | 1 | 26 | Setup environment | Kasun |  | 0%
NOT YET STARTED | HIGH | 29/9/2025 | 30/9/2025 | 1 | 27 | Deploy backend and front end to the prod environment | Kavinda. Kasun |  | 0%
NOT YET STARTED | HIGH | 30/9/2025 | 2025-01-10 | 1 | 28 | Upload mobile application to playstore and app store | Kasun |  | 0%
NOT YET STARTED | MEDIUM | 2025-02-10 | 2025-03-10 | 1 | 29 | Run prod test | Mila |  | 0%
NOT YET STARTED | MEDIUM | 2025-04-10 | 2025-06-10 | 2 | 30 | Create handover documentation | Sahan |  | 0%
NOT YET STARTED | MEDIUM | 2025-07-10 | 2025-09-10 | 2 | 31 | Create training materials | Sahan |  | 0%
NOT YET STARTED | LOW | 2025-10-10 | .. | .. | 32 | Monitor matrics | Mila |  | 0%
NOT YET STARTED | LOW | 2025-10-10 | .. | .. | 33 | Plan for future implementations | Sahan |  | 0%